## Project Timeline
Project-Schedule
Course | 40.015 Simulation Modeling and Analysis |  |  | Project Group Number | [8 empty] | Group 30
Member | Chi Ziheng, Wu Qi, Ryan Wong Jun Wei, Sabari Ganesan |  |  | Due Date | [8 empty] | Sunday 13th December, 23:59pm
Timetable |  |  | Detail
|  |  |  | Week5 | [6 empty] | Week6 | [6 empty] | Week7 | [6 empty] | Week8 | [6 empty] | Week9 | [6 empty] | Week10 | [6 empty] | Week11 | [6 empty] | Week12 | [5 empty] | Week13 | [6 empty] | Week14
|  |  |  | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | Sa | Su | M | T | W | T | F | Sa | Su | M | T | W | T | F | Sa | Su
| Member's work update: | Phases |  | Week5 M: Phase 1; Week7 M: Phase 2; Week9 M: Phase 3; Week12 M: Phase4
1 | Wu Qi | Responsibility: Data collection and manipulation; Simulation Design; Output Analysis | - objectives | Week5 M: Explore possible topics; Week6 M: Decide on one topic; Week7 M: Start learning Simio; Week8 M: Try basic logic in Simio; Week9 M: Finish Simio online toturial; Week10 M: Revise Simio toturial; Week11 M: Consult Simio documentation for logic adding; Week12 M: Testing model running and gather output data |  | Prepare slides and wrap up output statistical analysis | [13 empty] | Project Presentation
|  |  | - deliverable | Week6 M: Choose modeling on study room; Week8 M: Built a simple animation flow; Week9 M: First protopyte of simio model; Week10 M: Extra features to simio prototype; Week11 M: Build first model outine; Week12 M: Functional model with sufficient logic and output data |  | Statistical analysis report and final version of simio model | [6 empty] | Project submission and presentation
|  |  | - consultation/confusion | Week6 M: Consult with prof Nuno; Week8 M: Regular Biweekly meeting; Week9 M: Regular Biweekly meeting; Week11 M: Regular Biweekly meeting |  | Regular Biweekly meeting
-
2 | Ryan Wong Jun Wei | Responsibility: Data collection and manipulation; Simulation Design; Output Analysis | - objectives | Week5 M: Explore possible topics; Week6 M: Decide on one topic; Week7 M: Start thinking about logic; Week8 M: Finish event graph; Week10 M: Consolidate model assumptions; Week12 M: Making title page |  | Finalize presentation deck
|  |  | - deliverable | Week6 M: Choose modeling on study room; Week9 M: Final verion of simulation desgin; Week11 M: Textual description of project; Week12 M: Final version of film cut | [8 empty] | Project submission and presentation
|  |  | - consultation/confusion | Week6 M: Consult with prof Nuno; Week8 M: Regular Biweekly meeting; Week9 M: Regular Biweekly meeting; Week11 M: Regular Biweekly meeting |  | Regular Biweekly meeting
-
3 | Chi Ziheng | Responsibility: Abstract and motivation; Background reading; Project management | - objectives | Week5 M: Explore possible topics; Week6 M: Decide on one topic; Week7 M: Start thinking about logic; Week8 M: Finish event graph; Week9 M: Finish Simio online toturial; Week10 M: Revise Simio toturial; Week11 M: Consult Simio documentation for logic adding; Week12 M: Testing model running and gather output data |  | Prepare slides and wrap up output statistical analysis
|  |  | - deliverable | Week6 M: Choose modeling on study room; Week9 M: First protopyte of simio model; Week10 M: Extra features to simio prototype; Week11 M: Build first model outine; Week12 M: Functional model with sufficient logic and output data |  | Statistical analysis report and final version of simio model | [6 empty] | Project submission and presentation
|  |  | - consultation/confusion | Week6 M: Consult with prof Nuno; Week8 M: Regular Biweekly meeting; Week9 M: Regular Biweekly meeting; Week11 M: Regular Biweekly meeting |  | Regular Biweekly meeting
-
4 | Sabari Ganesan | Responsibility: Title page; User interface visualization and Animation | - objectives | Week5 M: Explore possible topics; Week6 M: Decide on one topic; Week7 M: Start learning Simio; Week8 M: Try basic logic in Simio; Week10 M: Enhance model animation; Week12 M: Prepare model documentation |  | Revise model output analysis
|  |  | - deliverable | Week6 M: Choose modeling on study room; Week9 M: Design model visualization; Week11 M: Output analysis question design |  | Statistical analysis report and final version of simio model | [6 empty] | Project submission and presentation
|  |  | - consultation/confusion | Week6 M: Consult with prof Nuno; Week8 M: Regular Biweekly meeting; Week9 M: Regular Biweekly meeting; Week11 M: Regular Biweekly meeting |  | Regular Biweekly meeting
-